# CWF One-Day Deployment Playbook

Target: Complete SharePoint infrastructure in a single working day using cwf_full_deploy.ps1

## Deployment Day Timeline

| Time | Phase | Action | Duration | Method |
| --- | --- | --- | --- | --- |
| 0800 | Prep | Create Teams Group, open SP site, install PnP.PowerShell | 30 min | Manual (Teams UI) |
| 0830 | Phase 1 | Run script: 16 lists + 190 columns created | 20 min | cwf_full_deploy.ps1 |
| 0850 | Phase 2 | Seed 73 DCWF roles + 49 certs + UIC map | 15 min | cwf_teams_sp_deploy.ps1 -SkipListCreation -SkipPermissions |
| 0905 | Phase 3 | Create 10 SP groups + 7-tier RBAC permissions | 10 min | cwf_full_deploy.ps1 (auto) |
| 0915 | Phase 4 | Create 40+ filtered views (installation, compliance, SAAR pipeline, certs) | 15 min | cwf_full_deploy.ps1 (auto) |
| 0930 | Phase 5 | Apply JSON column formatting (status badges, date highlighting) | 10 min | cwf_full_deploy.ps1 (auto) |
| 0940 | Phase 6 | Create data ingestion folder structure (/Inbox, /Processed, /Failed) | 5 min | cwf_full_deploy.ps1 (auto) |
| 0945 | Break | Coffee. Review validation report CSV. | 15 min |  |
| 1000 | Phase 7 | Validate: review report, fix any errors, re-run failed phases | 15 min | cwf_full_deploy.ps1 -StartPhase 7 |
| 1015 | Manual | Apply site-level sensitivity label (SP Admin Center → Policies tab) | 10 min | SP Admin Center |
| 1025 | Manual | Apply list-level sensitivity labels via PnP (run label script) | 15 min | PnP PowerShell |
| 1040 | Manual | Add users to SP groups: your identity to System Admins, ISSMs to their groups | 30 min | SP Site Settings |
| 1110 | Flows | Build Flow F-D: Dispatcher (file → detect report type → route) | 45 min | Power Automate |
| 1155 | Flows | Build Flow F-A: Report A processor (training → CWF lists) | 60 min | Power Automate |
| 1255 | Lunch |  | 30 min |  |
| 1325 | Flows | Build Flow F-B: Report B processor (SAAR → CWF lists) | 60 min | Power Automate |
| 1425 | Flows | Build 5 sync flows (F1–F5: SP → Dataverse) from Migration Guide | 90 min | Power Automate |
| 1555 | Flows | Build 6 notification flows (F6–F11: cert expiry, SAAR approval, etc.) | 90 min | Power Automate |
| 1725 | Test | Export 2 small reports from Power BI, drop in /Inbox/, verify end-to-end | 30 min | Manual + monitoring |
| 1755 | Package | Screenshot everything for STIG compliance package | 30 min | Manual |
| 1825 | Done | All infrastructure deployed, tested, documented. |  |  |

TOTAL WORKING TIME: ~10.5 hours. Phases 1–7 (scripted) take ~80 minutes. Sensitivity labels and user assignment take ~55 minutes. The 14 Power Automate flows take ~5.5 hours. Testing and documentation take ~1 hour.

## Quick-Reference Commands

Copy-paste these in order. Each is a single command.

### Step 1: Full Automated Deploy

.\cwf_full_deploy.ps1 -SiteUrl "https://[tenant].sharepoint-mil.us/sites/TACOMG-6CWFCompliancePortal"

### Step 2: Seed Reference Data

.\cwf_teams_sp_deploy.ps1 -SiteUrl "https://[tenant].sharepoint-mil.us/sites/TACOMG-6CWFCompliancePortal" -SkipListCreation -SkipPermissions

### Step 3: Resume After Failure

# Resume from Phase 3 (skips Phases 1-2): .\cwf_full_deploy.ps1 -SiteUrl "..." -StartPhase 3 # Re-run only validation: .\cwf_full_deploy.ps1 -SiteUrl "..." -StartPhase 7

### Step 4: Sensitivity Labels

# After running full deploy, apply labels: Set-PnPSite -SensitivityLabel "<CUI-GUID>" Set-PnPList -Identity "CWF_Personnel" -SensitivityLabelId "<CUI-Secured-Internal-GUID>" Set-PnPList -Identity "CWF_SAAR" -SensitivityLabelId "<CUI-Recipients-Only-GUID>" Set-PnPList -Identity "CWF_Configuration" -SensitivityLabelId "<CUI-Recipients-Only-GUID>" # ... repeat for all 16 lists per Migration Guide Section 3.3

## JSON View Formatting Reference

The script auto-applies these formatters in Phase 5. This reference shows what each one does for manual adjustments.

| List | Column | Format Type | Visual Effect |
| --- | --- | --- | --- |
| CWF_Personnel | cwf_compliance_status | Status Badge | Green pill = Compliant, Red = Non-Compliant, Yellow = Partial, Gray = Pending |
| CWF_PersonnelCerts | cwf_pc_cert_status | Status Badge | Green = Active, Red = Expired, Yellow = Expiring Soon |
| CWF_PersonnelCerts | cwf_pc_exp_date | Date Highlight | Red background if <30 days, Yellow if <90 days, Bold+red text if past due |
| CWF_PersonnelTraining | cwf_pt_status | Status Badge | Green = Completed, Red = Expired/Failed, Blue = In Progress |
| CWF_PersonnelTraining | cwf_pt_exp_date | Date Highlight | Same as cert expiration date formatting |
| CWF_SAAR | cwf_saar_wf_status | Pipeline Badge | Green = Fully Approved, Blue = Submitted, Gray = Draft, Red = Denied/Revoked |
| CWF_SAAR | cwf_saar_exp_date | Date Highlight | Red/Yellow expiration highlighting |
| CWF_STIGCompliance | cwf_stig_severity | CAT Badge | Red = CAT I, Orange = CAT II, Green = CAT III, Gray = Informational |
| CWF_POAM | cwf_poam_severity | CAT Badge | Same as STIG severity |
| CWF_Waivers | cwf_waiver_exp_date | Date Highlight | Expiration highlighting on waivers |
| CWF_Systems | cwf_sys_ato_exp | Date Highlight | ATO expiration highlighting |

### Manual JSON Application (if needed)

If the script fails to apply formatting on a column, apply it manually:

# In SharePoint: # 1. Open the list # 2. Click the column header dropdown → "Column settings" → "Format this column" # 3. Click "Advanced mode" # 4. Paste the JSON from the script’s Phase 5 variables # 5. Click "Save" # Or via PnP PowerShell: $json = Get-Content ".\formatting\compliance_badge.json" -Raw $field = Get-PnPField -List "CWF_Personnel" -Identity "cwf_compliance_status" $field ¦ Set-PnPField -Values @{ CustomFormatter = $json }

## Complete View Inventory

Phase 4 creates these views automatically. Total: 40+ views across all lists.

| Category | Views Created | Lists Applied To |
| --- | --- | --- |
| Installation Filters (7×4=28) | TACOM HQ, TACOM HQ G6, ANAD, RRAD, WVA, RIA-JMTC, SIAD | Personnel, PersonnelCerts, PersonnelTraining, SAAR |
| Supervisor | My Direct Reports (filtered by cwf_supervisor_email = [Me]) | Personnel |
| Compliance Status (4) | Compliant, Non-Compliant, Partially Compliant, Expired | Personnel |
| Cert Expiration (2) | Expiring in 90 Days, Expired Certs | PersonnelCerts |
| SAAR Pipeline (4) | Draft, Submitted, Fully Approved, Denied | SAAR |
| STIG (2) | Open Findings, CAT I Findings | STIGCompliance |
| POA&M (2) | Open POA&Ms, Overdue POA&Ms | POAM |

SETTING DEFAULT VIEWS: After the script runs, you can set any view as the default for a specific group by navigating to List Settings → Views → select the view → check “Make this the default view.” For ISSMs, set their installation view as default. For supervisors, set “My Direct Reports” as default on CWF_Personnel.